Module 2 — Task Checklist

Abu Dhabi Impact Evaluation Training  ·  Oct 12–15, 2026

☑ = done   ☐ = to do.  Tags show who owns each task.

| FK | Fiona | LUCAS | Lucas |
| --- | --- | --- | --- |
| ASK | Waiting on someone/something |  |  |

SESSION OWNERSHIP — agreed 23 Sep 2026

Owner is accountable for the session end to end; the other person is the second pair of eyes and reviews the live deck.

LUCAS   Oct 12 S1 · Oct 12 S3 · Oct 13 S2 · Oct 14 S1 · Oct 14 S3 · Oct 15 S2

FIONA   Oct 12 S2 · Oct 13 S1 · Oct 13 S3 · Oct 14 S2 · Oct 15 S1 · Oct 15 S3

Lucas reviews Fiona's six sessions; Fiona reviews Lucas's six.

All twelve decks are built and published. An owner is not the builder: the decks were built by Claude, and git history records who wrote what.

Still open on delivery: real case data for four decks (Oct13 S1 DOH, Oct13 S2 DCD, Oct13 S3 DCD Case 2, Oct14 S1 cost case), the Menti codes, and the four 2-hour sessions being short of their slide budget (Oct12 S3 26, Oct13 S3 25, Oct14 S3 23, Oct15 S3 18 slides).

GENERAL — across all sessions

☐   FK   Run the AI questions/tasks myself to capture examples of bad vs good responses

☐   FK   Think about ways to incorporate our "AI for IE" slides (and exercises, if we have any)

☐   FK   Review wording across the materials to make sure it is clear but also not too simple

☐  ASK · SEBASTIAN/MONICA/LUCAS  Are the sessions too long? What to prioritize vs cut? How can we improve the formatting (should we use ppt instead of quarto)?

DAY 1 · Oct 12

Session 1 — Compared to What? / Know the Language First

☑   FK   Drafted by FK

☐   FK   Review the draft – need more detail and graphs to explain pval, CIs, etc.

Session 2 — Abu Dhabi Police (descriptives)

☑   LUCAS   Build the session

Session 3 — Spot the Problem / Naive Comparisons & RCT

☑   FK   Drafted by FK using old material

☑   FK   Review the draft

☐   LUCAS   Add the Abu Dhabi Police findings from Session 2 into the placeholder (as a comparison) once we have them

DAY 2 · Oct 13  (one programme, four methods)

Session 1 — DiD (Reading DiD Results)

☑   FK   Drafted by FK

☐   FK   Review; consider shortening further

☑   FK   Compare the new version against the old one to make sure nothing important/better is missing

☐   LUCAS   Add the case study (framed as an exercise for participants: description, code, and a few questions to answer)

Session 2 — RDD (Reading RDD Results)

☑   FK   Draft with Claude

☐   FK   Review the draft

☐   LUCAS   Add the case study

Session 3 — Matching (Reading Matching Results)

☑   FK   Draft with Claude, including PSM and CEM

☐   FK   Review the draft

☐   ASK · SEBASTIAN/MONICA/LUCAS  do we want to keep PSM and CEM or just one of these?

☐   LUCAS   Add the case study

DAY 3 · Oct 14

Session 1 — Cost Analysis

☑   LUCAS   Build the session

Session 2 — Data Visualisation

☑   LUCAS   Build the session

Session 3 — "Interrogate the Analyst" QA Clinic

☑   LUCAS   Build the session - do we have an existing QA checklist in mind?

☐   FK   Check my notes for some critical questions I think they should ask AI

☐   FK   May be a good place to add some AI content

DAY 4 · Oct 15

Session 1 — Is This Evidence Credible? / QA Deep Dive

☑   LUCAS   Build the session

Session 2 — From Findings to Policy / Evidence Translation (1.5 hrs)

☐   FK   Draft with AI how this would look over 1.5 hrs, for PwC to support in creating

☐   ASK · SCO   Ask SCO whether they have a favourite (or a few favourite) policy briefs as examples of an ideal one

☐   FK   Review the draft

Session 3 — Plan Your Own Evaluation (building on Module 1)

☐   FK   Draft with Claude

☐   ASK · SEBASTIAN/MONICA   Ask Sebastian / Monica for their Module 1 slides, especially on evaluation design and evidence translation/use

☐   FK   Review the draft

All twelve sessions are built and published. Checked items are drafts that exist; the review passes, the PwC materials and the case studies that await real data all remain open.